## Slide 1
Advertise project (Elders newsletter
Local libraries)
Ageing Creatively: visual schema for Fieldwork, data collection and analysis
Programme:
Taster session
(Stage 2 consent)
&
10 sessions
Participants reflections:
-refreshment time
- Personal diaries or blog
Research team contact Participants with information leaflet, questionnaire, consent form
(stage 1 consent)
Performance
1 Group facilitator session
Pre workshop Individual
Questionnaire (phone)
Participant Symposium:
all participants/facilitators: Present initial findings to , discuss, validate & expand’
Post workshop Individual
Questionnaires
1-10 weeks
(Sept-Dec)
Final month of study
6 Group discussions
Weekly Team meetings to reflect on process and adjust
Weekly Team meetings: analysis
‘Exit strategy’: all participants provided information on follow up courses
Workshops
Designing workshops
Facilitators reflections:
-weekly post workshop
evaluation
Post Workshops (immediate) Jan
Post Workshops)
(feb- march 2013
Research seminar (presenting findings/draft final report)
Interested individuals respond to flyer provide contact details